Mayo Local Authorities

Disability Implementation Plan

2008 – 2015

Alternative Formats

This document is available in Accessible HTML format from the www.mayococo.ie website or in alternative formats, upon request.

Disability Implementation Plan 2008 - 2015

Table of Contents

1.0	INTRODUCTION.	3

1.0.1	Implementation Plan	5

1.1	APPROACH	6

1.1.1	Resources	7

1.1.2	Consultation	8

1.1.3	Inter Agency Co-operation	9

1.1.4	Role of external expertise	9

1.1.5	Disability awareness/equality training	9

1.2	ACCESS AUDITS	11

1.2.1	Access to Public Buildings.	11

1.2.2	Access to Services.	12

1.2.3	Accessibility of Services Supplied to a Public Body	13

1.2.4	Access to information	14

1.2.5	Inquiry Officers	16

1.2.6	Employment in Public Service	17

1.3	PRIORITISATION	18

2.0	Action Matrix	20

2.1	Buildings Action Matrix	21

2.2	I.T. Action Matrix	64

2.3	North East Region Action Matrix	66

2.4	South East Region Action Matrix	96

2.5	West Region Action Matrix	99

2.6	Training Action Matrix	126

2.7	Annual Cost Summary	128

PART 1

Disability Implementation Plan

2008 – 2015

# INTRODUCTION.

#### The Disability act 2005 is designed to support the provision of disability specific services and to improve access to mainstream public services for people with disabilities. It provides a statutory basis for accessible public buildings and services, the six sectoral plans, positive action for the employment in the public service, and restrictions on the use of genetic information, and the establishment of a centre for excellence in universal design.

Mayo Local Authorities are fully committed to meeting its obligations under the Disability Act 2005.  This Act requires the four Local Authorities of Mayo (Mayo County Council and the Town Councils of Ballina, Castlebar and Westport) to provide people with disabilities full and equal access to all their services.

Under the Department of Environment, Heritage and local Government Sectoral Plan each Local Authority is required to prepare an Implementation Plan for the County. The Implementation Plan will be underpinned by a commitment to funds by the Government, to ensure its implementation.

The plan provides information on measures to be taken to facilitate access by persons with disabilities to information, services, public roads, public places and buildings thus ensuring the Authorities services, programs, and facilities are as accessible to people with disabilities as they are to the rest of the community.

- The Authorities mission is:

“To improve the quality of life for people living in Mayo and enhance the attractiveness of Mayo as a place in which to live in, work, enjoy, visit and invest”.

This means it has a responsibility to provide services in a manner that promotes equitable participation by, and outcomes for, people with disabilities.

Our commitment to develop and maintain the built environment will allow people with a disability to have better opportunities in life and break the cycles of disadvantage and dependency. We recognise that it is not only the built environment that can act as a barrier to participation or engagement in the use of our services but also that attitudinal approaches can play a part. With this in mind we will ensure that staff and Members of Mayo Local Authorities are adequately trained to provide effective and non-discriminatory services and employment options for people with disabilities.

As a signatory to the Barcelona Declaration, Mayo Local Authorities have a proven track record based on the principle of Social Inclusion. At present, people with a disability, in Mayo Local Authorities, make up 6% of the total staff numbers, which is twice the minimum requirement set out in the Disability Act 2005.

The work carried out by Mayo Local Authorities, promotes, and actively encourages, equal opportunities for persons with disabilities; this allows them to participate in the economic, social, and cultural life of our communities.

As a result of the work being carried out, Mayo Local Authorities have won five major awards in 2007

- The O2 Ability Award –overall winner for the public sector.

- Three Awards from the NDA Excellence through Accessibility Awards in 2007.

- An E-Government Award for our website.

## Implementation Plan

- The plan is composed of two parts;

- Part 1, outlining our objectives and how we are going to implement them.

- Part 2, refers to the issues identified in recent accessibility audits of publicly accessible buildings, footpath networks, parks, cemeteries and open spaces.

# APPROACH

We in Mayo Local Authorities recognise and acknowledge the importance and value of accessible facilities and services.  We aim to provide a co-ordinated approach to the provision of these facilities and services. To achieve this, an internal working group has been established. The group is called the Access for All Committee (AFAC). The Access for All Committee will be a key player in the Disability Implementation Plan.  It will provide advice and guide the evaluation process.

The Committee was established in April 2006, with representation from all Directorates and disabled staff. It is an internal working group, headed up by The Director of Corporate Affairs. Members of the committee come from a wide cross-section within the Authority. Membership of this committee may be obtained, upon request, from the Access Officer, or via the Accessibility Section of the County Councils website.

The Terms of Reference for the Committee are:

- “To initiate, promote, create awareness and implement universal access policies in the four Mayo Local Authorities and to manage, co-ordinate and oversee the implementation of the policies and associated actions in compliance with current legislation”.

The responsibilities of the Committee are:

- To motivate other staff in the four Local Authorities and to assist them to develop appropriate responses to the access needs of people with disabilities;

- To review where the Authorities stands in relation to disability awareness measures, approaches and skills, implementation plans, support structures and staff skills;

- To plan and have carried out access audits of all public facilities in the four Local Authorities;

- To plan and put in place an implementation plan to bring the four Local Authorities public services and facilities to a standard that are useable by all.

- To ensure that accessibility is embedded across the organisation and integral to corporate plans and general business planning.

- To guide activities within the organisation, including the optimal spending of monies allocated by the DEHLG to ensure services and facilities are accessible for all.

## Resources

Mayo Local Authorities have benefited from the funding provided through the Department of Environment Heritage and Local Government (DEHLG) for the National Disability Strategy. The monies received through this source have been used to provide accessibility training and some of the audits on our facilities. It has been used to commence works on some priority issues, including improved accessible facilities at many road junctions throughout the County. It has also been used to enhance access in Aras an Chontae, public libraries, leisure centers and other public buildings.  There are still very many areas that require attention and through the accessibility audits carried these out these works have been identified and will be progressed with additional funding applied for from the DEHLG as required.

The AFA Committee will allocate and monitor financial resources as approved by the Department Of Environment Heritage and Local Government. Priority will be given to local authority buildings and other facilities to which access is most frequently required as well as accessible public footpaths, streets and crossings in urban areas. The plans will set out targets and timeframes for carrying out these works to reflect local priorities.

## Consultation

An essential component of the plan will be to ensure that consultation with relevant bodies is developed and maintained, and in this regard a Disability Forum has been established. This is a consultation mechanism whereby registered disabled organisations meet and consult under the auspices of Community and Enterprise (C&E).  To further enhance the consultation mechanism joint meetings of the Access for All Committee/Disability Forum have been formally established.

A draft of this implementation plan was circulated to disabled organisations within the County and made available to interested parties for comments and suggestions. An Access for All Committee/Disability Forum consultation meeting was held where further comments and suggestions were sought prior to the plan being finalised.

Mayo Local Authorities have several employees with visual and motor impairments.  To date, the IT Department has asked these staff members to review internal and external applications to ensure that they are easy to use for customers utilising assistive technology.  During our 2006 IT Accessibility audit, we ensured that user testing was carried out including users availing of several forms of assistive technology.  We intend to include similar users in future audits.

Going forward, we hope to liaise more directly with organisations members who avail of different assistive technologies to include them more fully in future redesigns of the websites.

## Inter Agency Co-operation

With regard to the built environment, it is the intention of the Mayo Local Authorities to provide access and adapt services to ensure people with disabilities do not experience discrimination as users of Mayo Local Authorities services, as service providers, or as staff, and that their particular needs of services and support are acknowledged and met. In this regard Mayo Local Authorities will work collaboratively with all of the other state agencies who may be working to different demands and constraints with a view to resolving the significant challenges or difficulties in coordinating timescales and milestones. e.g. we will engage with Bus Eireann and Iranród Eireann with a view to improving the accessibility features of the public transport systems that serve the Mayo Local Authorities area. The Health Services Executive (HSE) and Department of Family Social and Community Affairs (DFSCA) are both represented on the Disability Forum and contribute to the development of enhanced accessible services for our customers.

## Role of external expertise

To make sure that Mayo Local Authorities remain at the forefront of developments in accessibility matters we will participate in the Equality Officers and the Access Officers networks supported by the LGMSB and other networks that have accessibility as one of their key concerns. We will continue to work closely with the NDA to develop good practice in accessibility issues.  We will continue to engage with all relevant bodies. We will continue to develop further networks and links with relevant agencies during 2008.

## Disability awareness/equality training

Mayo Local Authorities will continue to support programmes of Equality Disability Awareness Training. In addition, staff and Members of Mayo Local Authorities will be trained to provide effective and non-discriminatory services and employment options for people with disabilities.

We recognise that it is not only the built environment that can act as a barrier to participation or engagement in the use of our services but also that attitudinal approaches can play their part. Providing information and services in a user-friendly way that responds to the needs of people with disabilities will increase customer satisfaction.

A department that understands the diverse needs of its customers will provide a better quality of service to all of its clients. In this regard Mayo Local Authorities commits to support all staff in acquiring the relevant skills and competencies to assist any person visiting or seeking service from us.  This will ensure staff are confident and competent in providing services for and managing people of all abilities.

# ACCESS AUDITS

## Access to Public Buildings.

Section 25 of the Act requires local authorities to ensure that all its public buildings are fully accessible, as far as practicable, to persons with disabilities. Buildings are required to be brought into compliance with Part M (Access for People with Disabilities) of the Building Regulations not later than 31 December 2015. The Department of the Environment, Heritage and Local Government Sectoral Plan requires Local Authorities to carry out accessibility audits of all roads and streets, pavements and pedestrian crossings, public buildings, public parks, amenities and open spaces, heritage sites, public libraries and harbours within its control and identify what remedial action is necessary to make these buildings and facilities accessible for people with disabilities.

To achieve this Mayo Local Authorities have completed accessibility audits on the Authority’s publicly accessible buildings and facilities and the list of works together with a time frame and assigned responsibility forms the basis of Part 2 to this document.

The Access audits have been carried out throughout the Authorities jurisdiction in part with the use of external consultants and in part by the Authorities own staff resources once appropriate training had been carried out. The access audit process has helped to raise awareness of disability access issues among all staff, and to the public. Significant long-term benefits will accrue from the Access Audit process. Mayo Local Authorities have now acquired an in -house accessibility awareness and auditing capacity in order to meet their obligations to disability proof new facilities, services and documentation in the future.

The current Technical Guidance document supporting the Part M Building Regulations is being redrafted. The Access for All Committee determined from the outset that Mayo Local Authorities would work towards the principles of universal accessibility and best practice. In order to attain this standard the audits were carried out to using a combination of best practice documents; the NDA document entitled “Building for everyone” and BS8300:2001,”Design of buildings and their approaches to meet the needs of disabled people-code of practice.”

Relevant members of the County Council Architects Department, together with technical staff have been given the opportunity to undertake accredited design accessibility auditing courses.

## Access to Services.

Section 26 of the Act requires that, from 31 December 2005, the Local Authority, where practicable and appropriate, shall ensure that the provision of access to the service by persons with and persons without disabilities is integrated. They shall provide for assistance, if requested, to persons with disabilities in accessing the service if the head of the body is satisfied that such provision is necessary in order to ensure compliance with this requirement. The Local Authority must also ensure the availability of persons with appropriate expertise and skills to give advice to the body about the means of ensuring that the service provided by the body is accessible to persons with disabilities, where appropriate. At least one Access Officer should be authorised to provide or arrange for and co-ordinate the provision of assistance and guidance to persons with disabilities in accessing its services.

To achieve this, Mayo Local Authorities require each line manager to ensure that the service or information that they are individually responsible for is delivered in all accessible formats. Managers responsible for the delivery of services and the supervision of staff, including those with disabilities together with line staff will be trained in the provision of accessible services. An Access Officer has been appointed to provide or arrange for and co-ordinate the provision of assistance and guidance to persons with disabilities in accessing its services.

Because of the large volume of customers that we serve and the range of those services, the very delivery of them requires uniformity and consistency to maintain good economic value and efficiency. However, not withstanding that requirement, Mayo Local Authorities will endeavour to be flexible with its systems or practices to take into account the requirements of people with disabilities.  All departments will be advised to be flexible, as far as is reasonably practicable with regard to the delivery of service to our customers with disabilities.

Mayo Local Authorities shall continue to work closely with the NDA, and other external organisations to develop good practice and ensure that the service provided by us is accessible to persons with disabilities.

## Accessibility of Services Supplied to a Public Body

Section 27 of the Act requires that, from 31 December 2005, the Local Authority shall ensure that, where a service is provided to a public body, the service is accessible to persons with disabilities, unless, it would not be practicable, would not be justified having regard to the cost of doing so, or would cause unreasonable delay in making the goods or services available to other persons.

This Mayo Local Authorities will, in future, try to ensure that all goods and services purchased are usable or adaptable for use by persons with disabilities. This will include furniture, fixtures and fittings, computer software and enhancements. When selecting venues for conferences or meetings we will ensure that they are accessible.   When awarding any contract we will ensure that accessibility considerations are taken into account and in particular when awarding built environment contracts, universal design and accessibility considerations will be addressed if appropriate.

We will ensure that accessibility procurement requirements are adhered to.

## Access to information

Section 28 of the Act requires that, from 31 December 2005, if the Local Authority communications are oral and the person or persons being communicated with has a hearing impairment and so requests, or, if the communication is a written one and the person or persons has a visual impairment and so requests, that, as far as practicable, the contents of the communication are communicated in a form that is accessible to the person concerned. Where the communications are in electronic form, the contents of the communication are to be accessible to persons with a visual impairment to whom adaptive technology is available, as far as practicable. Information published by the Authority, which contains information relevant to persons with intellectual disabilities, is to be in a clear language that is easily understood by those persons.

All staff have been informed that regularly used day to day documents are to be available in alternative formats.  An advise note stating “This document is available in Accessible HTML format from the www.mayococo.ie website or in alternative formats, upon request” will be printed inside the front and/or back covers of the document.

In accordance with the Disability Act 2005, the National Disability Strategy, NDA Electronic Accessibility Guidelines, the Barcelona Declaration and Mayo County Council disability policies, the IT Section endeavours to make all online information fully Accessible.

Mayo County Council uses four types of Accessibility auditing for its websites and electronic content:

- All content is spot checked by IT Staff trained in Accessibility before it goes live on the website.

- All websites are periodically checked using the NDA-recommended TAW automated testing tool.  This is used to highlight web pages that must be manually checked and/or pages with obvious Accessibility defects.

- All websites are periodically reviewed by IT Staff trained in Accessibility to ensure that pages meet Accessibility checkpoints which must be human-checked.

- The largest website, Mayococo.ie, is audited by an outside firm specialising in Accessibility approximately every 12-18 months.

All public web-based systems developed by Mayo County Council’s IT Section either directly in-house or by outside consultants are expected to meet the WAI AA level of Accessibility.  To ensure that this is done, 80% of the Web Team have received Accessibility training so that systems are designed to be Accessible.  During the testing of all new systems, staff evaluate new developments using both automated testing tools and manual checks in accordance with NDA recommendations.

Content published to the Mayo Local Authority websites undergoes two levels of auditing, in addition to in-built Accessibility features in the Content Management System.  Members of the Web Team spot check all content published to the various websites to avoid the publishing of non-Accessible content.  Periodically, IT Staff audit the websites using both automated and manual methods.  The largest website, Mayococo.ie is also regularly audited by an outside specialist.

Corporate documents are published in a variety of manners using both internal and external content providers and publishers.  The IT Section acts as an internal consultant who can advise and assist all Council Sections in ensuring that their final documents are Accessible.  In recent years, the Corporate Plan and the Annual Report have been published by the IT Section directly.

Starting in 2008, training will be made available to all interested staff to enable them to better create Accessible online documents as well as Accessible publications.

Our web site, which is already in operation, has to date won an E Government Award. The website will continue to be maintained at the highest accessibility level (WCAG: AA standard or AAA where practical).

## Inquiry Officers

Section 39 of the Act states that at least one Inquiry Officer may be authorised to perform the functions conferred on inquiry officers. Procedures are required to be drawn up in relation to the making and investigation of complaints and such other matters relating to complaints.

Mayo Local Authorities have authorised an inquiry officer to investigate and report on complaints made in relation to the failure of the Authority to comply with Section 25, 26, 27, 28 or 29 of the Act. Procedures have been drawn up in relation to the making and investigation of complaints. These procedures have been published and are available, upon request, or directly from the www.mayococo.ie website.

## Employment in Public Service

Section 47of the Act requires the Authority, in so far as practicable, to take all reasonable measures to promote and support the employment by it of persons with disabilities. The Authority shall ensure, unless there is good reason to the contrary for not doing so, that not less than 3 per cent of the persons employed by it are persons with disabilities.

Mayo Local Authorities has already actively encouraged the employment of people with disabilities. The current level of employment of people with disabilities is 6% which is twice the minimum requirement set out in the Disability Act 2005.

Mayo Local Authorities offer reasonable accommodations to staff with disabilities via their line manager. Staff with disabilities are encouraged to integrate and socialise with other staff at every opportunity.

# PRIORITISATION

The DEHLG Sectoral Plan states that “priority will be given to local authority buildings and other facilities to which access is most frequently required as well as accessible public footpaths streets and crossings in urban areas. The plans will set out targets and timeframes for carry out these works to reflect local priorities.”

Mayo local authorities are subdivided into there Regions for operational purposes. Each region has a Director of Services with responsibility for operational matters. The capital works programme is also managed by a Director of Services. The implementation plan is sub-divided into a number of sections whereby each Directorate may ensure their respective areas of responsibility are progressed. The prioritisation of planned works for each section is based upon the requirements of the Sectoral Plan.

Priority ratings are dependent upon health and safety issues, feasibility, number of people likely to be affected, cost and ease of implementation. The priority ratings used are:

Priority 1: Where failure to implement changes could significantly impede or prevent access and/or where a serious health and safety risk exists.

Priority 2: Where an access problem can be alleviated or make improvements that will have a considerable impact.

Priority 3: To improve access and/or where there is a reasonable high cost implication.

Priority 4: Implementation will improve access in the future.

Priority M: Where access is restricted due to the lack of suitable management plan or procedure.

Priority E: Where a shortfall is noted within an area only accessed by employees. Action required when an employee with a disability will work in this area and they are affected by the shortfall.

Priority Ma: Where an item can be addressed during routine maintenance.

The Sectoral Plan requires that Local Authorities will review and update their implementation plans and monitoring arrangements as necessary every three years, having regard to progress achieved, current priorities and resources and the balance of works to be completed up to 2015. This implementation plan principally concentrates on priority 1 works, based upon audits carried out, over a three year period 2008 to 2010. In some instances outlines of work planned between 2011 and 2015 are provided.  Review of the implementation plan in three years will identify and re-prioritise additional works based upon the audits.

Mayo County Council’s overall philosophy for electronic Accessibility is to make as many web pages and documents available in an Accessible format as possible.  Thus, we strive to ensure that all new electronic content is as Accessible as possible.  This includes key Council documents such as the Corporate Plan and the Annual Report.

However, when the provision of an Accessible document will require considerable time and the potential audience for that document is thought to be small, then the document will only be provided in an Accessible format upon request.  These types of documents include technical reports, documents from third-parties (e.g. state agencies), scanned images, etc.

The only online facilities which will be deployed in an inherently in-Accessible format will be those which will have a great deal of value to non-disabled users, but which cannot be provided in an Accessible format.  These include a very small number of applications—primarily map-based tools whose output is entirely visual.  In these instances, alternative channels for users to access the same information will be highlighted and these systems will be made to meet as many WAI checkpoints as possible to cater for as many users as possible.

The prioritisation of any of any remedial works identified by the audits may be adjusted following a consultation process with the joint Access for All Committee/Disability Forum. They may have regard to the levels of usage, the fit or coherence, with other agencies, the local authorities’ budgetary position and other local circumstances.

PART 2

Disability Implementation Plan

2008 – 2015

# Action Matrix

  - Buildings

  - I.T.

  - North East Region

  - South East Region

  - West Region

  - Training

  - Summary

# Buildings Action Matrix

SCHEDULE OF PUBLIC OFFICES & FACILITIES AUDITED .

OFFICES:

| PREMISES | CLASSIFICATION | CONSULTANT |
| --- | --- | --- |
| Aras an Chontae Complex, Castlebar | A | HKTT |
| Ballina Civic Offices | A | HKTT |
| Westport Civic Offices | A | HKTT |
| Swinford Area Office | B | CONFIGURE |
| Belmullet Civic Centre & Library. | B | CONFIGURE |
| Glenpark Complex. | B | CONFIGURE |
| Derrinumera Landfill & Civic Amenity | B | CONFIGURE |
| Rathroeen Landfill & Civic Amenity | B | CONFIGURE |
| Lough Lannagh Complex | B | CONFIGURE |
| Claremorris Area & Housing Offices | C | IN HOUSE |
| Newport Area Office | C | IN HOUSE |
| Ballinrobe Area & Housing Offices. | C | IN HOUSE |
| County Development Board/County Enterprise/Arts Offices Moneen. | C | IN HOUSE |
| Castlebar Town Council – Marsh House | C | IN HOUSE |
| County Development Board/County Enterprise/Arts - new Offices Cedar Building. | C | IN HOUSE |

SWIMMING POOLS

| PREMISES | CLASSIFICATION. | CONSULTANT |
| --- | --- | --- |
| Westport | A | IN HOUSE |
| Ballina | B | CONFIGURE |
| Castlebar | C | IN HOUSE |
| Claremorris | C | IN HOUSE |

LIBRARIES

| PREMISES | CLASSIFICATION. | CONSULTANT |
| --- | --- | --- |
| Ballina | A | CONFIGURE |
| Castlebar | B | IN HOUSE |
| Achill Library & Shared Services | B | CONFIGURE |
| Ballinrobe | B | IN HOUSE |
| Crossmolina | B | IN HOUSE |
| Foxford | B | IN HOUSE |
| Kiltimagh | B | IN HOUSE |
| Kilkelly | B | IN HOUSE |
| Westport | B | CONFIGURE |
| Charlestown Library & Regional Arts Centre | B | IN HOUSE |
| Ballyhaunis | C | IN HOUSE |
| Louisburgh | C | IN HOUSE |
| Claremorris | C | IN HOUSE |
| Swinford | C | IN HOUSE |

FIRE STATIONS

| PREMISES | CLASSIFICATION. | CONSULTANT |
| --- | --- | --- |
| Fire Station, HQ, Castlebar. | B | IN HOUSE |

PROGRAMME:

Mayo Local Authorities public buildings and facilities noted above have been categorised in terms of priority as follows:

Class A	High priority: relating to buildings of high public

usage requiring immediate implementation of recommended works (2008 to 2010).

Class B	Medium priority: requiring selective short-term actions (2008 to 2010) and completion of recommended works by 2015.

Class C	Low priority: requiring either no immediate works (relocation plans within 2yrs) or selective short-term actions

(Relocation plans within 5yrs).

All building implementation programmes proposed are based on the assumption that adequate resources, manpower and financial, are available to meet the commitments contained within this plan.

EXPENDITURE PROFILE 2008 to 2015

Classification:				2008 to 2010		2011 to 2015

___________________________________________________________

Class A Facilities				€1,320,000		€150,000

Class B Facilities				€590,000		€325,000

Class C Facilities				€20,000		€200,000

___________________________________________________________

Sub – Totals					€1,930,000		€675,000

Overall expenditure proposed	 2008 to 2015 is €2,605,000.

FUNDING

Funding in the amount of €2,605,000 is required to implement in full the recommendations of the building audits carried out to date.

Note: Costs quoted are based on current 2007 rates.

Premises:		Aras an Chontae Complex

Priority:			Class   A

Implementation:     2008-2015

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the ARAS | Ongoing to 2010 | Expenditure to date €750,000 Expenditure to end 2010 €600,000. | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Emergency Egress plans and procedures updated and incorporated into Access Handbook (which has been completed and dissimilated). Improvement works to date have centred on the main ground floor public entrances, foyers, wc facilities and circulation routes and building approaches. | Subject to budget approval, complete prioritised works to council chamber, first and second floors and escape routes. |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the RTC 1 | 2008 to 2010 | 300,000 | Architects Dept | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA RTC Manager. | Tender documentation prepared on recommended improvement works. | Subject to budget approval, Prioritised works to be tendered early 2008 |
| Priority rated 1, 2 & 3 works scheduled in audits. | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the RTC 2 | 2008 to 2010 | 150,000 | Architects Dept | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA RTC Manager. | Improvement works to date have centred on the automation of the main public entrances. | Subject to budget approval, complete prioritised works to building. |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the GWS OFFICE | 2011 to 2015 | 50,000 | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Audit complete and signage in progress. | Subject to budget approval, Prioritised works to be tendered early 2011 |
| Priority rated M, E & Ma. Works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the WORKSHOPS & STORES. | 2011 to 2015 | 50,000 | Architects Dept | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Audit complete. | Subject to budget approval, Prioritised works to be tendered early 2011 |
| Priority rated M & E works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the MACHINERY YARD OFFICES | 2011 to 2015 | 50,000 | Architects Dept | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Audit complete | Subject to budget approval, Prioritised works to be tendered early 2011 |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the CAR PARK | On going to 2007 | Expenditure to date €243,000 | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Works due for completion Dec 2007. |  |

Premises:		Ballina Civic Offices.

Priority:			Class   A

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within the Ballina Civic Offices. | 2008 to 2010 | Expenditure to end 2010 €160,000. | Ballina Town Council. | Corporate Affairs Dept IT Dept Planning Dept. Architects Dept. Access for All committee. Fire Services | Prioritised improvement works have been integrated into a major refurbishment proposal for the civic offices. Works to commence early 2008. | Subject to Budget approval, Contract signing and execution of the works. Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). |

Premises:		Westport Civic Offices.

Priority:			Class   A

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to priority 1 works to improve accessibility to and within the Westport Civic Offices. | On-going to 2007. |  | Westport Town Council. | Corporate Affairs Dept Dept Planning Dept. Architects Dept. Access for All committee. Fire Services. | Improvement works to date have centred on the main public entrance, foyer, circulation routes and building approaches. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). |
| Priority rated 2 works Scheduled in audit. | Review recommendations of audit report in relation to priority 2 works, implementing key items within the Westport Civic Offices. | 2008 to 2010 | €10,000 | Westport Town Council | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Key priority 1 works have been completed. The current building is a leased facility. Proposals regarding the development of new Civic Offices are well advanced with a timeframe of delivery within the next 5yrs. The extent of Priority 2 works to be to be undertaken will reflect the above situation. | Subject to budget approval, implement selected priority 2 works. |

Premises:		Ballina  Public Library

Priority:			Class   A

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Ballina Public Library. | Ongoing to 2011 | Expenditure to date €45,000 Estimated Expenditure to end 2011 €50,000. | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Emergency Egress plans and procedures updated and incorporated into Access Handbook (which has been completed and dissimilated). Improvement works to date have centred on the main ground floor public entrances, foyers, wc facilities, circulation routes, building approaches and signage. | Subject to budget approval, complete works to refuge zones, review tactile surfacing at stairways, and incorporate additional signage. |

Premises:		Westport Leisure Centre.

Priority:			Class   A

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within the Westport Leisure Centre | Ongoing to 2011 | Expenditure to date €95,000 Estimated Expenditure to end 2011 €50,000. | Westport Town Council. | Manager Westport Leisure Centre. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Emergency Egress plans and procedures updated and incorporated into Access Handbook (which has been completed and dissimilated). Improvement works to date have centred on the ground floor public entrances, foyers, building facilities, circulation routes, approaches and signage. | Subject to budget approval, completion of all priority works. |

Premises:		Ballina Public Swimming Pool.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1 works to improve accessibility to and within the Ballina Pool facility. | 2009 to 2010 | Estimated Expenditure to end 2010 €30,000. | Ballina Town Council. | Pool management committee. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete. | Emergency Egress plans to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, complete priority 1 works. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Ballina Pool facility | 2011 to 2015 | €30,000 | Ballina Town Council. | Pool management committee. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. |  | Subject to budget approval, complete scheduled priority 2 & 3 works. |

Premises:		Rathroeen Landfill Site.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1 works to improve accessibility to and within the Rathroeen Landfill Facility. | 2009 to 2010 | Estimated Expenditure to end 2010 €15,000. | Ballina Directorate. | Manager of Landfill site. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete. | Emergency Egress plans to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, complete priority 1 works. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 within the Rathroeen Landfill Facility. | 2011 to 2015 | Estimated Expenditure to end 2015 €20,000. | Ballina Directorate. | Manager of Landfill site. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. |  | Subject to budget approval, complete scheduled priority 2 & 3 works. |

Premises:		Swinford Area Offices.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1 works to improve accessibility to and within the Swinford Area Offices. | 2009 to 2010 | Estimated Expenditure to end 2010 €30,000. | Ballina Directorate. | Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete. | Emergency Egress plan to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval – tender and complete priority 1 works. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 within the Swinford Area Offices. | 2011 to 2015 | Estimated Expenditure to end 2015 €40,000. | Ballina Directorate. | Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, tender and complete scheduled priority 2 & 3 works. |

Premises:		Castlebar Public Swimming Pool.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 & 2 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1 & 2 works to improve accessibility to and within the Castlebar Pool facility. | 2008 to 2015 | Estimated Expenditure to end 2015 €15,000. | Castlebar Town Council. | Architects Dept. Pool management committee. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete. This existing pool facility is to be replaced with a new modern facility which is at preliminary design stage. Delivery timeframe of new facility is 5yrs. | Emergency Egress plans to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, complete selective priority 1 & 2works only. |

Premises:		Claremorris Public Swimming Pool.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | No works proposed to the existing Claremorris Pool facility. |  |  | Architects Dept. | Pool management committee. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | This existing pool facility is to be demolished and replaced by a new modern facility, which is currently awaiting Dept approval to proceed to contract signing stage. Delivery timeframe of new facility is 2yrs. | Subject to budget approval, contract signing and execution of the works on new facility. |

Premises:		County Board,Community & Enterprise  & Arts Offices, Moneen.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | No works proposed to the existing office facility at Moneen. |  |  | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | This existing office facility is to be vacated and relocated to new offices currently at fit-out stage. Delivery timeframe of new facility is 2 months. | Audit of new facility is in progress. Implement recommendations of new audit report when prepared to ensure accessibility to and within this new office facility. |

Premises:		Charlestown  Public Library & Regional Arts Centre.

Priority:			Class   B

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Charlestown Public Library & Arts Centre. | 2009 to 2010 | Estimated Expenditure to end 2010 €50,000. | Architects Dept. | Ballina Directorate. Co. Librarian Arts Officer. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services NDA | Prioritised improvement works are to be integrated into a major refurbishment proposal for the existing town hall to the rear of the library facility, which will transform same into a modern theatre, and arts centre. Currently at Part 8 Consultation stage. Delivery timeframe of new facility is 2 years. | Subject to a successful Part 8 process and budget approval, Tender action, Contract signing and execution of the works. Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). |

Premises:		Claremorris Area & Housing Offices.

Priority:			Class   C

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | No works proposed to the existing Area office and Housing office (Thornhill) in Claremorris |  |  | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Audits complete. The 2 existing office facilities are to replace by a new modern facility, which is to be tendered in early December 2007. Delivery timeframe of new facility is 12 months. | Tender project. Contract signing, early Jan 2008. Complete works by Dec 2008. Emergency Egress plans and procedures to be prepared and incorporated into Access Handbook (which when complete is to be dissimilated). |

Premises:		Ballinrobe Area & Housing Offices.

Priority:			Class   C

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | No works proposed to the existing Area office and Housing office in Ballinrobe |  |  | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Audits complete. The 2 existing office facilities are to be replaced by a new modern facility, which is currently on site and due for completion in June 2008. | Complete new office facility by June 2008. Emergency Egress plans and procedures to be prepared and incorporated into Access Handbook (which when complete is to be dissimilated). |

Premises:		Newport Area Office.

Priority:			Class   C

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | No works proposed to the existing Area office in Newport. |  |  | Architects Dept. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | The existing area office is to be relocated to a new office facility, which is currently under refurbishment. Delivery timeframe of new facility is 2 months. | Complete works by Dec 2007. Emergency Egress plans and procedures to be prepared and incorporated into Access Handbook (which when complete is to be dissimilated). |

Premises:		Belmullet Civic Centre & Library.

Priority:			Class   B

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1, 2 & 3 works to improve accessibility to and within the Belmullet Civic Office complex. | 2008 to 2010 | Estimated Expenditure to end 2010 €20,000. | Architects Department. | Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | The building Audit of the above building was carried out while the building was still under construction – and many of the recommendations contained within the report were incorporated into the facility during completion works. | Emergency Egress plan to be prepared and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, complete outstanding priority 1,2 & 3 works. |

Premises:		Glenpark Office Complex.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1 works to improve accessibility to and within the Glenpark Office complex | 2008 to 2010 | Estimated Expenditure to end 2010 €30,000. | Architects Dept. | Access Officer. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete. | Emergency Egress plan to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, tender and complete priority 1 works. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 within the Glenpark Office complex. | 2011 to 2015 | Estimated Expenditure to end 2015 €30,000. | Architects Dept. | Access Officer. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. |  | Subject to budget approval, tender and complete scheduled priority 2 & 3 works. |

Premises:		Derrinumera Landfill Site.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audit. | Implement recommendations of audit report in relation to scheduled priority 1 works to improve accessibility to and within the Derrinumera Landfill Facility. | 2008 to 2010 | Estimated Expenditure to end 2010 €15,000. | Ballina Directorate. | Manager of Landfill site. Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete. | Emergency Egress plans to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, tender and complete priority 1 works. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 within the Derrinumera Landfill Facility. | 2011 to 2015 | Estimated Expenditure to end 2015 €25,000. | Ballina Directorate. | Manager of Landfill site. Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. |  | Subject to budget approval, tender and complete scheduled priority 2 & 3 works. |

Premises:		Lough Lannagh Complex

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the MACALLA HALL & ANNEXE | 2009 to 2010 | €20,000 | Castlebar Town Council. | Architects Dept. Corporate Affairs Dept MCC IT Dept MCC Planning Dept. Access for All committee. Fire Services Complex manager. | Audits complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which has been completed and dissimilated). Subject to budget approval, Prioritised works to be tendered early 2009 |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the HOSTEL | 2009 to 2010 | 30,000 | Castlebar Town Council. | Architects Dept. Corporate Affairs Dept MCC IT Dept MCC Planning Dept. Access for All committee. Fire Services Complex manager | Audit complete. | Subject to budget approval, Prioritised works to be tendered early 2009 |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the FITNESS CENTRE | 2011 to 2015 | 30,000 | Castlebar Town Council. | Architects Dept. Corporate Affairs Dept MCC IT Dept MCC Planning Dept. Access for All committee. Fire Services Complex manager | Audit complete. | Subject to budget approval, Prioritised works to be tendered early 2011. |
| Priority rated 1, 2 & 3 works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the ACCESSIBLE COTTAGES (2NO) | 2011 to 2015 | 30,000 | Castlebar Town Council. | Architects Dept. Corporate Affairs Dept MCC IT Dept MCC Planning Dept. Access for All committee. Fire Services Complex manager | Audit complete. | Subject to budget approval, Prioritised works to be tendered early 2011 |
| Priority rated M, E & Ma. Works scheduled in audits | Implement recommendations of audit reports in relation to prioritised works to improve accessibility to and within the CARAVAN PARK | 2011 to 2015 | 15,000 | Castlebar Town Council. | Architects Dept. Corporate Affairs Dept MCC IT Dept MCC Planning Dept. Access for All committee. Fire Services Complex manager | Audit complete. | Subject to budget approval, Prioritised works to be tendered early 2011 |

Premises:		Castlebar Fire Station HQ.

Priority:			Class   B

Implementation:     2008-2010.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1, 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority works to improve accessibility to and within Castlebar Fire Station HQ facility. | 2009 to 2010 | €120,000. | Architects Dept. | Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | Building Audit complete on existing facility. | Emergency Egress plans to be updated and incorporated into the Access handbook (which when complete is to be dissimilated). Subject to budget approval, Priority 1,2 & 3 works to be tendered early 2009. |

Premises:		Achill Public Library & Shared Services

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Achill Public Library & shared service area. | 2009 to 2010 | €15,000. | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered early 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Achill Public Library & Shared service area. | 2011 to 2015 | €15,000 | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered early 2011. |

Premises:		Westport Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Westport Public Library. | 2009 to 2010 | €15,000. | Westport Town Council. | Co. Librarian Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered early 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Westport Public Library | 2011 to 2015 | €15,000 | Architects Dept. | Co. Librarian Architects Dept. Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered early 2011. |

Premises:		Crossmolina Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Crossmolina Public Library. | 2009 to 2010 | €15,000. | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered in 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Crossmolina Public Library | 2011 to 2015 | €10,000 | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered in 2011. |

Premises:		Ballinrobe Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Ballinrobe Public Library. | 2009 to 2010 | €40,000. | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered in 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Ballinrobe Public Library | 2011 to 2015 | €10,000 | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered in 2011. |

Premises:		Castlebar Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Castlebar Public Library. | On –going to 2010 | €50,000. | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. Recommendations contained in the above audit in relation to signage, automation of entrances, accessible public counter have been completed. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval – out-standing Priority 1 works to be tendered in 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Castlebar Public Library | 2011 to 2015 | €20,000 | Architects Dept. | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Outstanding Priority 2 & 3 works to be tendered in 2011. |

Premises:		Foxford Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Foxford Public Library. | 2009 to 2010 | €20,000. | Ballina Directorate | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered in 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Foxford Public Library | 2011 to 2015 | €10,000 | Ballina Directorate | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered in 2011. |

Premises:		Kiltimagh Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Kiltimagh Public Library. | 2009 to 2010 | €30,000. | Ballina Directorate | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered in 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Kiltimagh Public Library | 2011 to 2015 | €5,000 | Ballina Directorate | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered in 2011. |

Premises:		Kilkelly Public Library.

Priority:			Class   B

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated 1 works scheduled in audits | Implement recommendations of audit report in relation to prioritised works to improve accessibility to and within Kilkelly Public Library. | 2009 to 2010 | €30,000. | Ballina Directorate | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Architects Dept. Access for All committee. Fire Services | Audit complete. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which is to be completed and dissimilated). Subject to budget approval, Priority 1 works to be tendered in 2009. |
| Priority rated 2 & 3 works scheduled in audit. | Implement recommendations of audit report in relation to priority 2 & 3 works to improve accessibility to and within the Kilkelly Public Library | 2011 to 2015 | €20,000 | Ballina Directorate | Co. Librarian Corporate Affairs Dept IT Dept Planning Dept. Architects Dept. Access for All committee. Fire Services |  | Subject to budget approval, Priority 2 & 3 works to be tendered in 2011. |

Premises:		Swinford Public Library.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated works scheduled in audits | Review recommendations of audit report in relation to priority works noted, implementing key items to improve accessibility to and within the Swinford Public Library. | 2008 to 2015 | €30,000 | Ballina Directorate | Co. Librarian Corporate Affairs Dept DOEHLG Planning Dept. Architects Dept. Access for All committee. Fire Services. | The current building is a leased facility. Proposals regarding the development of a new Public library, in conjunction with a new cultural centre are advancing with a timeframe of delivery within the next 5yrs. The extent of Priority works to be to be undertaken in the short term will reflect the above situation. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). Subject to budget approval, implement selected priority works. |

Premises:		Ballyhaunis Public Library.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated works scheduled in audits | Review recommendations of audit report in relation to priority works noted, implementing key items to improve accessibility to and within the Ballyhaunis Public Library. | 2008 to 2015 | €30,000 | Architects Dept. | Co. Librarian Corporate Affairs Dept DOEHLG Planning Dept. Access for All committee. Fire Services. | Proposals regarding the refurbishment and extension of this library facility are advancing with a timeframe of delivery of same within the next 5yrs. Accessibility recommendations will be incorporated in future proposals. The extent of Priority works to be to be undertaken in the short term will reflect the above situation. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated. Subject to budget approval, implement selected priority works. |

Premises:		Claremorris Public Library.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated works scheduled in audits | Review recommendations of audit report in relation to priority works noted, implementing key items to improve accessibility to and within the Claremorris Public Library. | 2008 to 2015 | €30,000 | Architects Dept. | Co. Librarian Corporate Affairs Dept DOEHLG Planning Dept. Access for All committee. Fire Services. | Proposals regarding the refurbishment and extension of this library facility are advancing with a timeframe of delivery on same within the next 5yrs. Accessibility recommendations will be incorporated in future proposals. The extent of Priority works to be to be undertaken in the short term will reflect the above situation. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). Subject to budget approval, implement selected priority works. |

Premises:		Louisburgh Public Library.

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated works scheduled in audits | Review recommendations of audit report in relation to priority works noted, implementing key items to improve accessibility to and within the Louisburgh Public Library. | 2008 to 2015 | €60,000 | Westport Directorate | Co. Librarian Corporate Affairs Dept DOEHLG Planning Dept. Architects Dept. Access for All committee. Fire Services | The current building is a leased facility. The extent of Priority works to be to be undertaken in the short term will reflect the above situation. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). Subject to budget approval, implement selected priority works. |

Premises:		Castlebar Town Council Offices (Marsh House).

Priority:			Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority rated works scheduled in audits | Review recommendations of audit report in relation to priority works noted, implementing key items to improve accessibility to and within the current Castlebar Town Council Offices. | 2008 to 2015 | €50,000 | Architects Dept. | Town Manager Access Officer Corporate Affairs Dept DOEHLG Planning Dept. Access for All committee. Fire Services. | Proposals regarding the provision of new Town Council Civic Offices are advancing with a timeframe of delivery for same within the next 5yrs. The extent of Priority works to be to be undertaken in the short term will reflect the above situation. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). Subject to budget approval, implement selected priority works. |

Premises:	County Board, Community & Enterprise  & Arts – Nes Offices, Cedar Building.

Priority:		Class   C

Implementation:     2008-2015.

| Priority Works | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage With | Detail of Progress to Date / Amendments to Action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority works scheduled in audits | Review recommendations of audit report with landlord in relation to priority works noted, implementing key items to improve accessibility to and within the proposed new offices. . | 2007 to 2008 | €20,000 | Architects Dept. | Landlord Corporate Affairs Dept IT Dept Planning Dept. Access for All committee. Fire Services. | This existing office facility is to be upgraded and fitted out to meet the requirements of the above new tenants Many of the accessibility issues highlighted in the audit report relate to ‘Landlord Issues’ – which must be addressed directly by the Landlord. Signage to be addressed by MCC. Delivery timeframe of new facility is 2 months. | Emergency Egress plans and procedures to be updated and incorporated into Access Handbook (which when complete is to be dissimilated). Subject to budget approval, implement priority works in relation to signage. |

# I.T. Action Matrix

I.T. Action Matrix

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Complete the rebuilding of “small” Mayo Local Authorities websites to meet WAI AA guidelines. | Start: Q1 2007 | Completion: Q4 2008 | €50k | IT Section | LA Sections owning the various websites. | 8 websites completed. | Complete remaining 5 websites. |
| 2. | Provide training to Council staff on making electronic content and publications more Accessible. | Start: Q2 2008 | Completion: Q1 2008 | €35k | IT Section | LA Sections who provide web content and/or publish documents. | Not Applicable | - Create course - Promote course - Deliver course |
| 3. | Continue periodic audits of Mayococo.ie and other LA websites. | ongoing | ongoing | €4k pa | IT Section | Outside consulting firms. | Audit scheduled for Q1 2008 | Review audit results and make repairs. |
| 4. | Evaluate software/methodology for large publications to improve document Accessibility. | Start: 2009 | Completion: 2009 | unknown | IT Section | To Be Decided | Our current policies date to 2006 so should not need to be reviewed until 2009. | Review and revise policies |

# North East Region Action Matrix

| Town | P-1 | P-2 | P-3 | P-4 | P-H | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Ballina | €438,171 | €357,758 | €36,790 |  |  | €832,719 |
| Foxford | €205,691 | €196,000 | €419,250 |  |  | €820,941 |
| Crossmolina | €85,388 | €34,404 | €248,528 |  |  | €368,320 |
| Bunnyconnelan | €24,128 | €48,356 | €242,875 |  |  | €315,359 |
| Moygownagh | €24,252 | €9,525 | €92,340 |  |  | €126,117 |
| Charlestown | €103,330 | €76,580 | €172,500 |  |  | €352,410 |
| Kilkelly | €57,520 | ,---- | €338,285 |  | €11,700 | €407,505 |
| Carracastle | €3,800 | €3,560 | €290,460 |  |  | €297,820 |
| Knockmore | €26,738 | ,---- | €54,000 |  |  | €80,738 |
| Attymass | €26,325 | €45,000 | €234,030 |  |  | €305,355 |
| Kilmovee | €7,570 | €25,200 | ,---- |  |  | €32,770 |
| Kincon | €345 | ,---- | €100,200 |  |  | €100,545 |
| Meelik | €8,645 | €28,600 | €49,760 |  |  | €87,005 |
| Midfield | €4,470 | €10,800 | €42,530 |  |  | €57,800 |
| Toomore | €890 | ,---- | €13,630 |  |  | €14,520 |
| Ballycastle | €12,883 | €1,768 | €113,220 |  |  | €127,871 |
| Killala | €288,587 | €428,700 | €493,330 |  | €40,000 | €1,250,617 |
| Kilasser | €6,770 | €10,800 | €12,330 |  |  | €29,900 |
| Bohola | €19,288 | €5,500 | €79,945 |  |  | €104,733 |
| Pontoon | €33,075 | €23,200 | €145,390 |  |  | €201,665 |
| Swinford | €174,161 | €50,100 | €196,810 |  |  | €421,071 |
| Lacken | €6,305 | €14,700 | €100,420 |  |  | €121,425 |
| Aughamore | €770 | €32,520 | €36,000 |  |  | €69,290 |
| Kiltimagh | €146,714 | €26,600 | €320,260 |  |  | €503,574 |
| Srtaide Cemetery | €570 | €141,360 | ,---- |  |  | €141,930 |
| Kinaffe Cemetery | €570 | ,---- | €6,000 |  |  | €6,570 |
| Doocastle Cemetery | €645 | ,---- | ,---- |  |  | €654 |
| Rathfran Cemetry | €130 | €225 | €70,000 |  |  | €70,355 |
| Ballysakerry Cemetery | €6,000 | €200 | €13,425 |  |  | €19,625 |
| Temple Cemetery | ,---- | €12,250 | ,---- |  |  | €12,250 |
| Glendaduff Cemetery | €6,555 | ,---- | €32,400 |  |  | €38,955 |
| Bunnafinglas Cemetery | €320 | ,---- | €1,100 |  |  | €1,420 |
| Downpatrick Head | ,---- | €3,840 | ,---- | €108,800 |  | €111,840 |
| Kilcummin Pier | €35,320 | ,---- | €86,000 |  |  | €43,920 |
| Moyne Abbey | ,---- | ,---- | ,---- |  | €56,000 | €56,000 |
| Rosserk Abbey | €320 | ,---- | ,---- |  | €35,800 | €36,120 |
| Errew Abbey | ,---- | ,---- | ,---- |  | €180,000 | €180,000 |
| Total | €1,756,246 | €1,587,546 | €4,041,808 | €108,800 | €323,500 | €7,749,709 |

Implementation Plan for the North East Directorate

Ballina Town Council

Priority 1

Total - €438171

| Year 1 | 2008 | P1 | €146,057 |
| --- | --- | --- | --- |
| Year 2 | 2009 | P1 | €146,057 |
| Year 3 | 2010 | P1 | €146,057 |

Priority 2,3,4

Total - €394,550

| Year 1 | 2011 | P2,3 | €78,910 |
| --- | --- | --- | --- |
| Year 2 | 2012 | P2,3 | €78,910 |
| Year 3 | 2013 | P2,3 | €78,910 |
| Year 4 | 2014 | P2,3 | €78,910 |
| Year 5 | 2015 | P2,3 | €78,910 |

Implementation Plan for the North East Directorate

Mayo County Council

Priority 1

Total - €1,465,795

| Year 1 | 2008 | P1 | €488,599 |
| --- | --- | --- | --- |
| Year 2 | 2009 | P1 | €488,599 |
| Year 3 | 2010 | P1 | €488,599 |

Priority 2,3,4

Total - €5,451,190

| Year 1 | 2011 | P2,3,4 | €1,090,238 |
| --- | --- | --- | --- |
| Year 2 | 2012 | P2,3,4 | €1,090,238 |
| Year 3 | 2013 | P2,3,4 | €1,090,238 |
| Year 4 | 2014 | P2,3,4 | €1,090,238 |
| Year 5 | 2015 | P2,3,4 | €1,090,238 |

Implementation Plan for the North East Directorate

Priority 1 Works Plan 2008 to 2010

| Priority | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ballina Town |  |  |  |  |  |  |  |
| 1 | Pearse Street 4 Crossings |  | € 9000 | Mayo County Council |  |  | Budget Approval |
|  | Footpath Re-Grade |  | € 1200 |  |  |  |  |
| 1 | O’Rahily Street 2 Crossings |  | €4300 | Mayo County Council |  |  | Budget Approval |
| 1 | Bury Street 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
|  | 1 Sign |  | €750 |  |  |  |  |
|  | 1 Footpath |  | €2350 |  |  |  |  |
| 1 | Lord Edward Street 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Kevin Barry Street 3 Crossing |  | €7230 | Mayo County Council |  |  | Budget Approval |
| 1 | James Connelly Street 2 Crossing |  | €4700 | Mayo County Council |  |  | Budget Approval |
|  | 1 Sign |  | €750 |  |  |  |  |
|  | 1 Parking |  | €2350 |  |  |  |  |
| 1 | Casemont Street Sign |  | €750 | Mayo County Council |  |  | Budget Approval |
| 1 | Cathedral Street 4 Crossings |  | €9250 | Mayo County Council |  |  | Budget Approval |
|  | 1 Footpath |  | €4000 |  |  |  |  |
|  | 1 Parking |  | €2100 |  |  |  |  |
|  | 1 Sign |  | €750 |  |  |  |  |
| 1 | Cathedral Close 4 Crossings |  | €9400 | Mayo County Council |  |  | Budget Approval |
| 1 | Emmet Street 1 Sign |  | €750 | Mayo County Council |  |  | Budget Approval |
|  | 1 Crossing |  | €2350 |  |  |  |  |
| 1 | Tolan Street 1 Crossing |  | €2350 | Mayo County Council |  |  | Budget Approval |
| 1 | Barrett’s Street 7 Crossings |  | €16450 | Mayo County Council |  |  | Budget Approval |
| 1 | Teeling Street 3 Crossings |  | €7050 | Mayo County Council |  |  | Budget Approval |
| 1 | Tone Street 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Market Road 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Humbert Street 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Pound Street 4 Crossings |  | €9400 | Mayo County Council |  |  | Budget Approval |
|  | 1 Sign |  | €750 |  |  |  |  |
| 1 | Killala Road 4 Crossings |  | €9400 | Mayo County Council |  |  | Budget Approval |
| 1 | Marian Cresent 2 Crossings |  | €4500 | Mayo County Council |  |  | Budget Approval |
| 1 | Circular Road 3 Crossings |  | €7050 | Mayo County Council |  |  | Budget Approval |
| 1 | Bothernasnup 3 Crossings |  | €7050 | Mayo County Council |  |  | Budget Approval |
|  | 1 Footpath |  | €3840 |  |  |  |  |
| 1 | Lansyn East 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Lansyn West 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Bothernasnup- Killala Rd 3 Crossings |  | €7050 | Mayo County Council |  |  | Budget Approval |
| 1 | Mc Dermott Street 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | Abbey Street 8 Crossings |  | €18800 | Mayo County Council |  |  | Budget Approval |
|  | 1 Parking |  | €2100 |  |  |  |  |
| 1 | Bunree Road 8 Crossings |  | €18800 | Mayo County Council |  |  | Budget Approval |
|  | 2 Footpath |  | €3850 |  |  |  |  |
| 1 | Tom Ruane Park 1 Sign |  | €750 | Mayo County Council |  |  | Budget Approval |
|  | 1 Footpath / Crossing |  | €5350 |  |  |  |  |
| 1 | Howley Street 1 Crossing |  | €2350 | Mayo County Council |  |  | Budget Approval |
| 1 | Lower Bridge 1 Crossing |  | €2350 | Mayo County Council |  |  | Budget Approval |
| 1 | Bachelor’s Walk 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
|  | 1 Parking |  | €2100 |  |  |  |  |
| 1 | Arbuckle Row 1 Crossing |  | €2350 | Mayo County Council |  |  | Budget Approval |
|  | 1 Footpath |  | €1500 |  |  |  |  |
| 1 | Nally Street 1 Parking |  | €2100 | Mayo County Council |  |  | Budget Approval |
|  | 2 Crossings |  | €4700 |  |  |  |  |
|  | Car Park 1 Parking |  | €2500 | Mayo County Council |  |  | Budget Approval |
|  | 1 Footpath |  | €2350 |  |  |  |  |
| 1 | Castle Court 3 Crossings |  | €7050 | Mayo County Council |  |  | Budget Approval |
|  | Ridgepool Village 1 Crossing |  | €2350 | Mayo County Council |  |  | Budget Approval |
| 1 | Plunkett Road 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
|  | 1 Footpath |  | €3000 |  |  |  |  |
| 1 | Greenhills 5 Crossings |  | €11750 | Mayo County Council |  |  | Budget Approval |
| 1 | Ard Na Ri 1 Crossing |  | €2350 | Mayo County Council |  |  | Budget Approval |
| 1 | Ferran Terrace 4 Crossings |  | €9400 | Mayo County Council |  |  | Budget Approval |
|  | 1 Sign |  | €750 |  |  |  |  |
| 1 | Fenian Row 12 Crossings |  | €28200 | Mayo County Council |  |  | Budget Approval |
| 1 | Convent Hill 4 Crossings |  | €9400 | Mayo County Council |  |  | Budget Approval |
| 1 | Childers Heights 14 Crossings |  | €32900 | Mayo County Council |  |  | Budget Approval |
| 1 | The Commons 9 Crossings |  | €21150 | Mayo County Council |  |  | Budget Approval |
| 1 | Moy Heights 8 Crossings |  | €18800 | Mayo County Council |  |  | Budget Approval |
| 1 | Church Mannor 3 Crossings |  | €7050 | Mayo County Council |  |  | Budget Approval |
| 1 | Shanaghty Heights / The Meadows 2 Crossings |  | €4700 | Mayo County Council |  |  | Budget Approval |
| 1 | The Moorings 7 Crossings |  | €16450 | Mayo County Council |  |  | Budget Approval |
|  | Total |  | €438170 |  |  |  |  |
| Foxford |  |  |  |  |  |  |  |
| 1 | Footpath Replacement and Maintenance |  | €121100 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €69950 |  |  |  |  |
|  | Car Parks |  | €3516 |  |  |  |  |
|  | Street Furniture Relocation and Removal |  | €12000 |  |  |  |  |
|  | Seating |  | €1200 |  |  |  |  |
|  | Street Works |  | €200 |  |  |  |  |
|  | Cemetery Work |  | €6725 |  |  |  |  |
| Crossmolina |  |  |  |  |  |  |  |
| 1 | Footpath Replacement and Maintenance |  | €3900 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €80648 |  |  |  |  |
|  | Car Parks |  | €2140 |  |  |  |  |
|  | Street Furniture Relocation and Removal |  | €100 |  |  |  |  |
|  | Signs |  | €600 |  |  |  |  |
| 1 | Bunnyconnellan Crossings Construction and Repair |  | €15488 | Mayo County Council |  |  | Budget Approval |
|  | Car Parks |  | €2320 |  |  |  |  |
|  | Gates |  | €6000 |  |  |  |  |
|  | Cemetery Work |  | €320 |  |  |  |  |
| 1 | Moygownagh Crossings Construction and Repair |  | €21252 | Mayo County Council |  |  | Budget Approval |
|  | Car Parks |  | €3000 |  |  |  |  |
| 1 | Charlestown Footpath Replacement and Maintenance |  | €24100 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €74220 |  |  |  |  |
|  | Car Parks |  | €2360 |  |  |  |  |
|  | Street Furniture Relocation and Removal |  | €150 |  |  |  |  |
|  | Gates |  | €2400 |  |  |  |  |
|  | Signs |  | €100 |  |  |  |  |
| 1 | Kilkelly Footpath Replacement and Maintenance |  | €1100 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €48000 |  |  |  |  |
|  | Car Parks |  | €2100 |  |  |  |  |
|  | Cemetery Work |  | €6320 |  |  |  |  |
| 1 | Carracastle Footpath Replacement and Maintenance |  | €1300 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €2200 |  |  |  |  |
|  | Signs |  | €300 |  |  |  |  |
| 1 | Knockmore Footpath Replacement and Maintenance |  | €10800 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €13128 |  |  |  |  |
|  | Car Parks |  | €640 |  |  |  |  |
|  | Signs |  | €400 |  |  |  |  |
|  | Cemetery Work |  | €1770 |  |  |  |  |
| 1 | Attymass Footpath Replacement and Maintenance |  | €19800 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €4000 |  |  |  |  |
|  | Steps |  | €230 |  |  |  |  |
|  | Car Parks |  | €1780 |  |  |  |  |
|  | Seating |  | €200 |  |  |  |  |
|  | Cemetery Work |  | €545 |  |  |  |  |
| 1 | Kilmovee Car Parks |  | €1000 | Mayo County Council |  |  | Budget Approval |
|  | Cemetery Work |  | €6570 |  |  |  |  |
| 1 | Kincon Car Parks |  | €320 | Mayo County Council |  |  | Budget Approval |
|  | Cemetery Work |  | €25 |  |  |  |  |
| 1 | Meelick Crossings Construction and Repair |  | €8000 | Mayo County Council |  |  | Budget Approval |
|  | Ramps |  | €29660 |  |  |  |  |
|  | Signs |  | €100 |  |  |  |  |
|  | Cemetery Work |  | €6545 |  |  |  |  |
| 1 | Midfield Crossings Construction and Repair |  | €4000 | Mayo County Council |  |  | Budget Approval |
|  | Cemetery Work |  | €470 |  |  |  |  |
| 1 | Toomore Steps |  | €1000 | Mayo County Council |  |  | Budget Approval |
|  | Car Parks |  | €320 |  |  |  |  |
|  | Cemetery work |  | €570 |  |  |  |  |
| 1 | Ballycastle Footpath Replacement and Maintenance |  | €1000 | Mayo County Council |  |  | Budget Approval |
|  | Crossing Construction and Repair |  | €9808 |  |  |  |  |
|  | Car Parks |  | €1380 |  |  |  |  |
|  | Street Furniture Relocation and Removal |  | €50 |  |  |  |  |
|  | Seating |  | €200 |  |  |  |  |
|  | Signs |  | €100 |  |  |  |  |
|  | Cemetery Work |  | €345 |  |  |  |  |
| 1 | Killala Footpath Replacement and Maintenance |  | €97450 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €105432 |  |  |  |  |
|  | Car Parks |  | €3700 |  |  |  |  |
|  | Seating |  | €500 |  |  |  |  |
|  | Picnic Areas |  | €600 |  |  |  |  |
|  | Signs |  | €200 |  |  |  |  |
|  | Cemetery Work |  | €10945 |  |  |  |  |
|  | Harbour Work |  | €69040 |  |  |  |  |
| 1 | Ross Beach Ramp, Picnic Area, Walls, Toilets |  | €97200 | Mayo County Council |  |  | Budget Approval |
|  | Signs |  | €400 |  |  |  |  |
|  | Accessible Parking |  | €320 |  |  |  |  |
| 1 | Kilasser Crossings Construction and Repair |  | €4000 | Mayo County Council |  |  | Budget Approval |
|  | Car Parks |  | €1500 |  |  |  |  |
|  | Seating |  | €400 |  |  |  |  |
|  | Cemetery Work |  | €870 |  |  |  |  |
| 1 | Bohola Footpath Replacement and Maintenance |  | €200 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €17128 |  |  |  |  |
| 1 | Car Parks |  | €640 |  |  |  |  |
|  | Gates |  | €1000 |  |  |  |  |
|  | Cemetery Work |  | €320 |  |  |  |  |
| 1 | Pontoon Footpath Replacement and Maintenance |  | €15100 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €14775 |  |  |  |  |
|  | Car Parks |  | €500 |  |  |  |  |
|  | Seating |  | €1400 |  |  |  |  |
|  | Beach Works |  | €1300 |  |  |  |  |
| 1 | Swinford Footpath Replacement and Maintenance |  | €10600 | Mayo County Council |  |  | Budget Approval |
| 1 | Crossings Construction and Repair |  | €148736 |  |  |  |  |
|  | Car Parks |  | €8605 |  |  |  |  |
|  | Street Furniture Relocation and Removal |  | €150 |  |  |  |  |
|  | Seating |  | €1300 |  |  |  |  |
|  | Signs |  | €600 |  |  |  |  |
|  | Cemetery Work |  | €320 |  |  |  |  |
|  | Playgrounds |  | €3800 |  |  |  |  |
| 1 | Lacken Car Parks |  | €960 | Mayo County Council |  |  | Budget Approval |
|  | Beach Works |  | €4800 |  |  |  |  |
| 1 | Cemetery Work |  | €545 |  |  |  |  |
| 1 | Aughamore Car Parks |  | €320 | Mayo County Council |  |  | Budget Approval |
|  | Cemetery Work |  | €450 |  |  |  |  |
| 1 | Kiltimagh Footpath Replacement and Maintenance |  | €42650 | Mayo County Council |  |  | Budget Approval |
|  | Crossings Construction and Repair |  | €98664 |  |  |  |  |
|  | Car Parks |  | €5020 |  |  |  |  |
|  | Seating |  | €4700 |  |  |  |  |
|  | Picnic Areas |  | €50 |  |  |  |  |
|  | Signs |  | €450 |  |  |  |  |
| 1 | Straid Cemetery Cemetery Work |  | €570 | Mayo County Council |  |  | Budget Approval |
| 1 | Kinaffe Cemetery Cemetery Work |  | €570 | Mayo County Council |  |  | Budget Approval |
| 1 | Doocastle Cemetery Cemetery Work |  | €395 | Mayo County Council |  |  | Budget Approval |
| 1 | Rathfran Cemetery Cemetery Work |  | €130 | Mayo County Council |  |  | Budget Approval |
| 1 | Ballysakerry Cemetery Cemetery Work |  | €6000 | Mayo County Council |  |  | Budget Approval |
| 1 | Glendauff Cemetery Cemetery Work |  | €6555 | Mayo County Council |  |  | Budget Approval |
| 1 | Bunnafinglas Cemetery Cemetery Work |  | €320 | Mayo County Council |  |  | Budget Approval |
| 1. | Kilcummin Pier Ramps |  | €34400 | Mayo County Council |  |  | Budget Approval |
|  | Car Parks |  | €320 |  |  |  |  |
|  | Harbour Work |  | €600 |  |  |  |  |
| 1 | Rosserk Abbey Car Parks |  | €320 | Mayo County Council |  |  | Budget Approval |
|  | Total |  | €1465795 |  |  |  |  |
| 2. | Arising from audit of Council’s website and consultation, project to improve accessibility of online planning application monitoring tool. | 2007 to 2008 | €35K | Director of Service with responsibility for IT projects. | IT Consultancy Firm. Director of Service with responsibility for Planning. | Project requirements agreed internally. Tender prepared. | Advertise tender, evaluate bids and initiate project. |
| 3. | Develop a new Procurement Policy incorporating requirements of the Disability Act 2005 to ensure procured goods and services are accessible. | 2008 | Nil | Director of Service Corporate Affairs | Council employees who are people with disabilities. | Nil | Form Working Group from relevant sections and agree Workplan. |

# South East Region Action Matrix

Implementation Plan for the South East Directorate

Priority 1 Works Plan 2008 to 2010

Castlebar Town Council

Priority 1

Total - €

| Year 1 | 2008 | P1 | €125,590 |
| --- | --- | --- | --- |
| Year 2 | 2009 | P1 | €125,590 |
| Year 3 | 2010 | P1 | €125,590 |

Priority 2,3,4

Total - €

| Year 1 | 2011 | P2,3 | € |
| --- | --- | --- | --- |
| Year 2 | 2012 | P2,3 | € |
| Year 3 | 2013 | P2,3 | € |
| Year 4 | 2014 | P2,3 | € |
| Year 5 | 2015 | P2,3 | € |

Mayo County Council

Priority 1,2,3,4

Total - €

| Year 1 | 2011 | P1,2,3 | € |
| --- | --- | --- | --- |
| Year 2 | 2012 | P1,2,3 | € |
| Year 3 | 2013 | P1,2,3 | € |
| Year 4 | 2014 | P1,2,3 | € |
| Year 5 | 2015 | P1,2,3 | € |

| Priority | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action | Next Step |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Castlebar Provide crossings, dropped kerbs and tactile paving | 2008 to 2010 | €298,300 | Mayo County Council | Castlebar Town Council |  | Budget Approval |
|  | Provide/Correct footpaths |  | €4,200 |  |  |  |  |
|  | Reduce excessive gradients |  | €2,280 |  |  |  |  |
|  | Maintain poorly maintained footpath |  | €8,500 |  |  |  |  |
|  | Provide footpath where not continued |  | €42,130 |  |  |  |  |
|  | Relocate light pole |  | €4,200 |  |  |  |  |
|  | Widen footpath or provide crossing |  | €2,350 |  |  |  |  |
|  | Cut back hedgerow where obstructing footpath |  | €200 |  |  |  |  |
|  | Provide adequate parking |  | €2,400 |  |  |  |  |
|  | Provide dropped kerbs and signage for disabled parking |  | €4,700 |  |  |  |  |
|  | Raise low level signs |  | €7,500 |  |  |  |  |

# West Region Action Matrix

Implementation Plan for the West Directorate

Priority 1 Works Plan 2008 to 2010

| Town | P-1 | P-2 | P-3 | P-4 | P-H | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Achill Sound |  |  | €38,400.00 |  |  | €38,400.00 |
| Ballycorrick |  | €12,000.00 |  |  |  | €12,000.00 |
| Ballycroy |  | €28,000.00 |  |  |  | €28,000.00 |
| Bangor Erris | €32,000.00 | €419,820.00 |  |  |  | €451,820.00 |
| Belmullet | €52,000.00 | €723,000.00 | €28,000.00 |  |  | €803,000.00 |
| Bertraw Beach |  | €81,000.00 |  |  |  | €81,000.00 |
| Binghamstown |  | €108,000.00 |  |  |  | €108,000.00 |
| Eachleim |  | €89,700.00 |  |  |  | €89,700.00 |
| Geesala |  |  | €24,000.00 |  |  | €24,000.00 |
| Lecakanvy | €35,100.00 |  |  |  |  | €35,100.00 |
| Lecakanvy Pier | €66,000.00 |  |  |  |  | €66,000.00 |
| Louisburgh Town |  | €40,800.00 | €202,800.00 |  |  | €243,600.00 |
| Murrisk Pier |  | €49,500.00 |  |  |  | €49,500.00 |
| Newport |  | €449,500.00 |  |  |  | €449,500.00 |
| Old Head |  | €40,500.00 |  |  |  | €40,500.00 |
| Roonagh Pier |  | €35,100.00 |  |  |  | €35,100.00 |
| Westport | €1,055,432.00 | €457,989.00 | €62,613.00 |  |  | €1,576,034.00 |
| Total | €1,240,532.00 | €2,534,909.00 | €355,813.00 | €0.00 | €0.00 | €4,131,254.00 |

Implementation Plan for the West Directorate

Westport Town Council

Priority 1

Total - €1,055,432

| Year 1 | 2008 | P1 | €351,810 |
| --- | --- | --- | --- |
| Year 2 | 2009 | P1 | €351,810 |
| Year 3 | 2010 | P1 | €351,810 |

Priority 2,3,4

Total - €520,602

| Year 1 | 2011 | P2,3 | €104,120 |
| --- | --- | --- | --- |
| Year 2 | 2012 | P2,3 | €104,120 |
| Year 3 | 2013 | P2,3 | €104,120 |
| Year 4 | 2014 | P2,3 | €104,120 |
| Year 5 | 2015 | P2,3 | €104,120 |

Mayo County Council

Priority 1

Total - €185,100

| Year 1 | 2008 | P1 | €61,700 |
| --- | --- | --- | --- |
| Year 2 | 2009 | P1 | €61,700 |
| Year 3 | 2010 | P1 | €61,700 |

Priority 2,3,4

Total - €2,370,120

| Year 1 | 2011 | P2,3,4 | €474,024 |
| --- | --- | --- | --- |
| Year 2 | 2012 | P2,3,4 | €474,024 |
| Year 3 | 2013 | P2,3,4 | €474,024 |
| Year 4 | 2014 | P2,3,4 | €474,024 |
| Year 5 | 2015 | P2,3,4 | €474,024 |

| Priority | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action | Next Step |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Westport Town |  |  |  |  |  |  |
| 1 | Altamount Street Footpath | 2008 to 2010 | €19,930 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 |  | 2011 to 2015 | €9,660 |  |  |  |  |
| 3 |  | 2011 to 2015 | €7,900 |  |  |  |  |
| 1 | 4 Crossing | 2008 to 2010 | €9,200 |  |  |  |  |
| 2 | 1 Crossing | 2011 to 2015 | €2,350 |  |  |  |  |
| 3 | 1 Crossing | 2011 to 2015 | €2,100 |  |  |  |  |
| 1 | 1 Parking | 2008 to 2010 | €2,350 |  |  |  |  |
| 2 |  | 2011 to 2015 | €2,000 |  |  |  |  |
| 2 | 1 Street Furniture | 2011 to 2015 | €530 |  |  |  |  |
| 1 | 1 Signs & Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | 1 Crossing/ Footpath | 2008 to 2010 | €3,450 |  |  |  |  |
| 1 | Fairgreen 3 Footpath | 2008 to 2010 | €10,494 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | 2 Footpath | 2011 to 2015 | €3,930 |  |  |  |  |
| 1 | Steps | 2008 to 2010 | €3,350 |  |  |  |  |
| 1 | Signs | 2008 to 2010 | €750 |  |  |  |  |
| 2 | 2 Seating | 2011 to 2015 | €4,000 |  |  |  |  |
| 2 | Parking | 2011 to 2015 | €2,450 |  |  |  |  |
| 1 | 2 Crossing | 2008 to 2010 | €4,700 |  |  |  |  |
| 1 | Mill Road 3 Crossing | 2008 to 2010 | €7,300 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 1 Footpath | 2008 to 2010 | €4,162 |  |  |  |  |
| 2 | Mill Street 1 Footpath | 2011 to 2015 | €4,400 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 3 | 1 Footpath | 2011 to 2015 | €2,800 |  |  |  |  |
| 2 | 2 Street Furniture | 2011 to 2015 | €1,060 |  |  |  |  |
| 1 | Signs | 2008 to 2010 | €750 |  |  |  |  |
| 3 | Seating | 2011 to 2015 | €2,300 |  |  |  |  |
| 2 | Parking | 2011 to 2015 | €2,350 |  |  |  |  |
| 2 | Ramps | 2011 to 2015 | €1,550 |  |  |  |  |
| 1 | 2 Crossings | 2008 to 2010 | €4,950 |  |  |  |  |
| 1 | Chestnut Grove Crossing | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Crossing | 2011 to 2015 | €4,500 |  |  |  |  |
| 1 | Footpath | 2008 to 2010 | €2,750 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €1,060 |  |  |  |  |
| 2 | Steps | 2011 to 2015 | €5,550 |  |  |  |  |
| 1 | Grove Park Crossing | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Crossing | 2011 to 2015 | €2,350 |  |  |  |  |
| 1 | Footpath | 2008 to 2010 | €3,932 |  |  |  |  |
| 1 | Mill Street/Car Park North Crossing | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Ramp | 2011 to 2015 | €1.750 |  |  |  |  |
| 1 | 1 Footpath | 2008 to 2010 | €4,910 |  |  |  |  |
| 2 | 3 Footpath | 2011 to 2015 | €5,950 |  |  |  |  |
| 2 | Steps | 2011 to 2015 | €4,000 |  |  |  |  |
| 1 | Steps/Ramps | 2008 to 2010 | €4,430 |  |  |  |  |
| 2 | Car Parks | 2011 to 2015 | €8,900 |  |  |  |  |
| 1 | Mill Street/Car Park South Crossing | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €6,450 |  |  |  |  |
| 1 | Car Park | 2008 to 2010 | €2,000 |  |  |  |  |
| 2 | Car Park | 2011 to 2015 | €620 |  |  |  |  |
| 1 | High Street 3 Footpath | 2008 to 2010 | €29,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 2 Crossing | 2008 to 2010 | €4,700 |  |  |  |  |
| 1 | Signs | 2008 to 2010 | €750 |  |  |  |  |
| 3 | Railway Walk Seating | 2011 to 2015 | €700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 3 | Signs | 2011 to 2015 | €750 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €2,000 |  |  |  |  |
| 1 | John’s Row Steps | 2008 to 2010 | €6,650 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €6,250 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €4,376 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | The Elms Footpath | 2008 to 2010 | €1,800 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Crossing | 2011 to 2015 | €2,150 |  |  |  |  |
| 3 | Seating | 2011 to 2015 | €1,500 |  |  |  |  |
| 1 | Prospect Avenue Crossing | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Steps | 2011 to 2015 | €650 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €4,550 |  |  |  |  |
| 1 | Hill side 2 Footpath | 2008 to 2010 | €6,230 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Peter Street Parking | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Steps | 2008 to 2010 | €6,400 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €1,060 |  |  |  |  |
| 1 | Quay Street Footpath | 2008 to 2010 | €2,520 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Footpath | 2011 to 2015 | €1,180 |  |  |  |  |
| 1 | Church Street Crossing | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Steps | 2011 to 2015 | €950 |  |  |  |  |
| 1 | Signs | 2008 to 2010 | €1,500 |  |  |  |  |
| 1 | The Octagon Footpath | 2008 to 2010 | €2,210 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Footpath | 2011 to 2015 | €1,180 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Parking | 2008 to 2010 | €2,350 |  |  |  |  |
| 3 | Shop Street Crossing | 2011 to 2015 | €2,150 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | James Street Footpath | 2011 to 2015 | €3,000 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 2 | Crossing | 2011 to 2015 | €4,300 |  |  |  |  |
| 1 | Parking | 2008 to 2010 | €2,350 |  |  |  |  |
| 2 | James Street Tourist Info Centre Signage | 2011 to 2015 | €750 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Footpath | 2008 to 2010 | €2,200 |  |  |  |  |
| 2 | Parking | 2011 to 2015 | €750 |  |  |  |  |
| 1 | James St. Car Park Crossing | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 2 Footpath | 2008 to 2010 | €5,202 |  |  |  |  |
| 2 | 2 Footpath | 2011 to 2015 | €2,100 |  |  |  |  |
| 1 | Car Park | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 2 | Steps | 2011 to 2015 | €6,900 |  |  |  |  |
| 1 | Leisure Centre, Cinema & Playground Footpath | 2008 to 2010 | €900 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | 3 Footpath | 2011 to 2015 | €3,090 |  |  |  |  |
| 3 | Gates | 2011 to 2015 | €250 |  |  |  |  |
| 2 | Steps | 2011 to 2015 | €6,350 |  |  |  |  |
| 3 | Steps | 2011 to 2015 | €8,350 |  |  |  |  |
| 2 | Ramps | 2011 to 2015 | €3,150 |  |  |  |  |
| 1 | Bridge Street Crossings | 2008 to 2010 | €8,600 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Parking | 2008 to 2010 | €4,450 |  |  |  |  |
| 3 | Street Furniture | 2011 to 2015 | €250 |  |  |  |  |
| 2 | Seating | 2011 to 2015 | €1,150 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €700 |  |  |  |  |
| 1 | North Mall 4 Crossing | 2008 to 2010 | €10,800 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 5 Footpath | 2008 to 2010 | €8,280 |  |  |  |  |
| 2 | 2 Footpath | 2011 to 2015 | €9,300 |  |  |  |  |
| 3 | 1 Footpath | 2011 to 2015 | €2,100 |  |  |  |  |
| 1 | Steps | 2008 to 2010 | €3,350 |  |  |  |  |
| 2 | Steps | 2011 to 2015 | €1,600 |  |  |  |  |
| 1 | Signs | 2008 to 2010 | €750 |  |  |  |  |
| 1 | South Mall Sign | 2008 to 2010 | €1,500 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Footpath | 2008 to 2010 | €2,700 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €2,100 |  |  |  |  |
| 2 | Castlebar Street Footpath | 2011 to 2015 | €1,015 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Crossing | 2008 to 2010 | €10,600 |  |  |  |  |
| 2 | Controls | 2011 to 2015 | €500 |  |  |  |  |
| 1 | Distillery Road Crossing | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €13,075 |  |  |  |  |
| 1 | Castlebar Rd N5 3 Crossing | 2008 to 2010 | €6,850 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 4 Footpath | 2008 to 2010 | €8,660 |  |  |  |  |
| 2 | 5 Footpath | 2011 to 2015 | €12,555 |  |  |  |  |
| 1 | Footpath/ Crossing | 2008 to 2010 | €7,110 |  |  |  |  |
| 1 | Fr. Angelus Park Footpath/ Crossing | 2008 to 2010 | €2,350 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €2,250 |  |  |  |  |
| 1 | Seating | 2008 to 2010 | €1,450 |  |  |  |  |
| 2 | Seating | 2011 to 2015 | €2,900 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Carrowbeg Estate & Allergan 7 Crossing | 2008 to 2010 | €16,450 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 2 Footpath | 2008 to 2010 | €7,650 |  |  |  |  |
| 1 | Footpath/ Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Newport Street Crossing | 2008 to 2010 | €2,850 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Crossing | 2011 to 2015 | €250 |  |  |  |  |
| 1 | Footpath | 2008 to 2010 | €1,060 |  |  |  |  |
| 1 | St. Mary’s Crescent & St. Mary’s Villas 4 Crossing | 2008 to 2010 | €9,200 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | 4 Crossing | 2011 to 2015 | €7,350 |  |  |  |  |
| 1 | 2 Footpath | 2008 to 2010 | €4,850 |  |  |  |  |
| 2 | 6 Footpath | 2011 to 2015 | €23,105 |  |  |  |  |
| 3 | 1 Footpath | 2011 to 2015 | €2,281 |  |  |  |  |
| 2 | 2 Parking | 2011 to 2015 | €3,400 |  |  |  |  |
| 2 | Controls | 2011 to 2015 | €250 |  |  |  |  |
| 1 | 2 Sign | 2008 to 2010 | €1,500 |  |  |  |  |
| 1 | Newport Road (R319) 3 Crossing | 2008 to 2010 | €7,050 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €2,350 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €3,000 |  |  |  |  |
| 1 | Crossing/ Footpath | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Steps/ Footpath | 2008 to 2010 | €3,900 |  |  |  |  |
| 1 | Steps | 2008 to 2010 | €8,750 |  |  |  |  |
| 1 | Ozanam Place & The Paddock 2 Crossing | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €6,500 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €1,150 |  |  |  |  |
| 3 | Parking | 2011 to 2015 | €2,350 |  |  |  |  |
| 1 | Glenlara Park 2 Crossing/ Footpath | 2008 to 2010 | €8,820 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Steps | 2008 to 2010 | €2,150 |  |  |  |  |
| 2 | Steps | 2011 to 2015 | €6,250 |  |  |  |  |
| 1 | 4 Footpath | 2008 to 2010 | €30,750 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €7,050 |  |  |  |  |
| 1 | Pinewoods 2 Crossings | 2008 to 2010 | €4,500 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Steps | 2011 to 2015 | €5,550 |  |  |  |  |
| 1 | Deerpark East 2 Crossing | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Footpath | 2011 to 2015 | €3,250 |  |  |  |  |
| 1 | King’s Hill 2 Crossings | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Crossing/ Steps | 2008 to 2010 | €5,400 |  |  |  |  |
| 1 | Footpath | 2008 to 2010 | €2,100 |  |  |  |  |
| 1 | Tober Hill Street 5 Footpath | 2008 to 2010 | €24,950 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Parking | 2008 to 2010 | €2,350 |  |  |  |  |
| 1 | Crossing | 2008 to 2010 | €2,350 |  |  |  |  |
| 3 | Seating | 2011 to 2015 | €2,700 |  |  |  |  |
| 2 | Quay Road Footpath | 2011 to 2015 | €1,890 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 2 Crossing | 2008 to 2010 | €4,700 |  |  |  |  |
| 1 | Leenane Road (N59) 3 Crossings | 2008 to 2010 | €7,050 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Reek View, St. Patrick’s Terrace, Pearse Terrace, McBride Terrace 4 Footpath | 2008 to 2010 | €58,400 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 3 | Mc Convill Community Playgroup Seating | 2011 to 2015 | €450 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Footpath | 2011 to 2015 | €2,200 |  |  |  |  |
| 1 | Westlands 7 Crossings | 2008 to 2010 | €16,450 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | 1 Crossing | 2011 to 2015 | €2,150 |  |  |  |  |
| 1 | Harbour Village 7 Crossing | 2008 to 2010 | €16,450 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | 2 Crossing | 2011 to 2015 | €5,060 |  |  |  |  |
| 1 | Footpath/Crossing | 2008 to 2010 | €9,850 |  |  |  |  |
| 2 | Footpath | 2011 to 2015 | €2,100 |  |  |  |  |
| 1 | Boffin Street Crossing | 2008 to 2010 | €2,150 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Footpath | 2008 to 2010 | €3,176 |  |  |  |  |
| 1 | Fairways 7 Crossings | 2008 to 2010 | €16,450 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Michael Davitt Park 2 Crossings | 2008 to 2010 | €4,700 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | Parnell Court 3 Crossings | 2008 to 2010 | €7,050 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Knockranny Village 2 Crossings | 2011 to 2015 | €14,100 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Knockranny Road 2 Footpaths | 2011 to 2015 | €70,040 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Ashwood 2 Footpaths | 2011 to 2015 | €5,000 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 1 | 3 Crossing | 2008 to 2010 | €6,750 |  |  |  |  |
| 2 | Crossing | 2011 to 2015 | €2,150 |  |  |  |  |
| 1 | General Signage | 2008 to 2010 | €4,000 | Mayo County Council | Westport Town Council |  | Budget Approval |
| 2 | Old Head Footpath | 2011 to 2015 | €40,500 | Mayo County Council |  |  | Budget Approval |
| 2 | Roonagh Pier Footpath | 2011 to 2015 | €35,100 | Mayo County Council |  |  | Budget Approval |
| 3 | Louisburgh Long Street Footpath | 2011 to 2015 | €97,800 | Mayo County Council |  |  | Budget Approval |
| 2 | Chapel Street Footpath | 2011 to 2015 | €40,800 |  |  |  |  |
| 3 | Footpath | 2011 to 2015 | €105.000 |  |  |  |  |
| 4 | Murrisk Pier Footpath | 2011 to 2015 | €49,500 | Mayo County Council |  |  | Budget Approval |
| 1 | Signage | 2008 to 2010 | €2,500 |  |  |  |  |
| 2 | Parking | 2011 to 2015 | €2,000 |  |  |  |  |
| 2 | Seating | 2011 to 2015 | €700 |  |  |  |  |
| 3 | Resurface Pier | 2011 to 2015 | €60,600 |  |  |  |  |
| 1 | Lecanvey Footpath | 2008 to 2010 | €117,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Newport Quay Road Footpath | 2011 to 2015 | €415,800 | Mayo County Council |  |  | Budget Approval |
| 3 | Footpath | 2011 to 2015 | €9,900 |  |  |  |  |
| 3 | Castlebar Road Cut Back Vegetation | 2011 to 2015 | €200 | Mayo County Council |  |  | Budget Approval |
| 1 | Newport Bridge Remove Lamp Posts | 2008 to 2010 | €2,500 | Mayo County Council |  |  | Budget Approval |
| 2 | Footpath | 2011 to 2015 | €39,000 |  |  |  |  |
| 2 | Main Street Removal of Bin | 2011 to 2015 | €500 | Mayo County Council |  |  |  |
| 2 | Footpath | 2011 to 2015 | €27,600 |  |  |  |  |
| 2 | Medalicott Street Removal of Bin | 2011 to 2015 | €1,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Georges Street Footpath | 2011 to 2015 | €3,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Main Street Opposite Centra | 2011 to 2015 | €1,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Quay Rd/George Street Footpath | 2011 to 2015 | €156,000 | Mayo County Council |  |  | Budget Approval |
| 3 | Quay Road Footpath | 2011 to 2015 | €216,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Lower Main St. Beside Newport House Crossing | 2011 to 2015 | €8,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Lower Main St. Beside Centra Crossing | 2011 to 2015 | €8,000 | Mayo County Council |  |  |  |
| 2 | Upper Main Street, Hotel Newport Crossing | 2011 to 2015 | €8,000 | Mayo County Council |  |  |  |
| 2 | Georges Street, Beside Tourist Office Crossings | 2011 to 2015 | €16,000 | Mayo County Council |  |  |  |
| 1 | Lower Castlebar St Beside Fire Station Steps | 2008 to 2010 | €2,000 | Mayo County Council |  |  |  |
| 2 | Main Street Opposite Taste Buds Steps | 2011 to 2015 | €1,000 | Mayo County Council |  |  |  |
| 4 | Street Furniture | 2011 to 2015 | €100 |  |  |  |  |
| 2 | Bertra Beach Footpath | 2011 to 2015 | €81,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Parking | 2011 to 2015 | €5,000 |  |  |  |  |
| 2 | Lifeguard Training | 2011 to 2015 | €8,000 |  |  |  |  |
| 1 | Lecanvey Pier Footpath | 2008 to 2010 | €66,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Signs | 2011 to 2015 | €2,500 |  |  |  |  |
| 2 | Ramps | 2011 to 2015 | €5,000 |  |  |  |  |
| 3 | Parking | 2011 to 2015 | €500 |  |  |  |  |
| 2 | Pier Surface is uneven | 2011 to 2015 | €68,400 |  |  |  |  |
| 3 | Belmullet Pearse Street 2 Footpaths | 2011 to 2015 | €1,000 | Mayo County Council |  |  | Budget Approval |
| 3 | Chapel Street 2 Footpaths | 2011 to 2015 | €600 | Mayo County Council |  |  | Budget Approval |
| 3 | Carter Square | 2011 to 2015 | €100 | Mayo County Council |  |  | Budget Approval |
|  | William Street (from Shore Rd to Post Office) Footpath | 2011 to 2015 | €40,500 | Mayo County Council |  |  | Budget Approval |
| 2 | William St (From Shore Rd to AIB) Footpath | 2011 to 2015 | €27,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Fr. Mulherin Crescent Footpath | 2011 to 2015 | €900 | Mayo County Council |  |  | Budget Approval |
| 2 | Corclough Road Footpath | 2011 to 2015 | €133,500 | Mayo County Council |  |  | Budget Approval |
| 2 | Industrial Estate to Secondary Schools Footpath | 2011 to 2015 | €366,600 | Mayo County Council |  |  | Budget Approval |
| 2 | R313 Blacksod Rd Footpath | 2011-‘15 | €186,900 | Mayo County Council |  |  | Budget Approval |
| 1 | Hospital Entrance to Bridge Footpath | 2008 to 2010 | €64,800 | Mayo County Council |  |  | Budget Approval |
| 3 | Bangor Erris Outside Parish Hall/Community Centre | 2011 to 2015 | €500 | Mayo County Council |  |  | Budget Approval |
|  | Main St at Health Centre & Barrett’s Garage Footpath |  |  |  |  |  |  |
| 1 | Springfield Estate Footpath | 2008 to 2010 | €118,800 | Mayo County Council |  |  | Budget Approval |
| 2 | Main Street Footpath | 2011 to 2015 | €110,400 | Mayo County Council |  |  | Budget Approval |
| 2 | Rd at Community Centre Footpath | 2011 to 2015 | €85,500 | Mayo County Council |  |  | Budget Approval |
| 2 | Church Rd/Bangor Bridge Footpath | 2011 to 2015 | €72,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Church Rd Footpath | 2011 to 2015 | €144,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Springfield Entrance 2 Crossings | 2011 to 2015 | €102,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Main Street Crossing | 2011 to 2015 | €8,000 | Mayo County Council |  |  | Budget Approval |
| 1 | Church Road Crossing | 2008 to 2010 | €32,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Bangor Graveyard | 2011 to 2015 | €8,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Parking | 2011 to 2015 | €320 |  |  |  |  |
| 3 | Hose | 2011 to 2015 | €100 |  |  |  |  |
| 3 | Compost | 2011 to 2015 | €25 |  |  |  |  |
| 2 | Binghamstown Footpath | 2011 to 2015 | €108,000 | Mayo County Council |  |  | Budget Approval |
| 2 | Eachleim 2 Footpaths | 2011 to 2015 | €89,700 | Mayo County Council |  |  | Budget Approval |
| 2 | 3 Crossing | 2011 to 2015 | €12,000 |  |  |  |  |
| 2 | Ballycorrick Footpath | 2011 to 2015 | €43,800 | Mayo County Council |  |  | Budget Approval |
| 2 | 2 Crossings | 2011 to 2015 | €12,000 |  |  |  |  |
|  | Achill Sound Footpath | 2011 to 2015 | €62,100 | Mayo County Council |  |  | Budget Approval |
| 2 | Crossings | 2011 to 2015 | €4,000 |  |  |  |  |
| 3 | Geesala Footpath | 2011 to 2015 | €388,800 | Mayo County Council |  |  | Budget Approval |
| 3 | 4 Crossings | 2011 to 2015 | €20,000 |  |  |  |  |
| 2 | Ballycroy Footpath | 2011 to 2015 | €60,600 | Mayo County Council |  |  | Budget Approval |
| 3 | 2 Footpaths | 2011 to 2015 | €129,600 |  |  |  |  |
| 2 | 7 Crossings | 2011 to 2015 | €28,000 |  |  |  |  |

# Training Action Matrix

Training Action Matrix

| Priority | Action & Sub-Tasks | Timeframe | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Provide training to Council staff on disability awareness and provision of accessible services. | 2008 to 2015 | €35,000 per annum | Corporate Affairs | All departments | Not Applicable | Create courses Promote courses Deliver courses |

# Annual Cost Summary

|  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Buildings | 643,333 | 643,333 | 643,333 | 135,000 | 135,000 | 135,000 | 135,000 | 135,000 |
| I.T. | 85,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 |
| N.E. Directorate | 634,656 | 634,656 | 634,656 | 1,169,148 | 1,169,148 | 1,169,148 | 1,169,148 | 1,169,148 |
| S.E. Directorate | 125,590 | 125,590 | 125,590 |  |  |  |  |  |
| West Directorate | 413,510 | 413,510 | 413,510 | 578,144 | 578,144 | 578,144 | 578,144 | 578,144 |
| Training | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 |
| TOTAL | 1,937,089 | 1,856,089 | 1,856,089 | 1,921,292 | 1,921,292 | 1,921,292 | 1,921,292 | 1,921,292 |